## Sheet1
Task # | Iteration | Module Name | RCT ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner
R2-I3
1 | R2-I3 | 02. Job Management | 2.05 | Apply | Allow user to apply for job opening | 2021-02-04 | 2021-06-04 | 100% | Nikhil, Ishaan
2 | R2-I3 | 02. Job Management | 2.05 | Apply | Send the user application to the recruiter | 2021-02-04 | 2021-06-04 | 100% | Nikhil, Ishaan
3 | R2-I3 | 02. Job Management | 2.05 | Apply | Crosscuts: Entitlements | 2021-02-04 | 2021-06-04 | 100% | Nikhil, Ishaan
4 | R2-I3 | 02. Job Management | 2.05 | Apply | Crosscuts: Connectivity | 2021-02-04 | 2021-06-04 | 100% | Nikhil, Ishaan
5 | R2-I3 | 02. Job Management | 2.05 | Apply | Crosscuts: DF-out, Security | 2021-02-04 | 2021-06-04 | 100% | Nikhil, Ishaan
6 | R2-I3 | 02. Job Management | 2.05 | Apply | Test 'Apply' feature | 2021-06-04 |  | 50% | Athauda
7 | R2-I3 | 04. Account Management | 4.01 | View My Account | Allow partners to view their account information | 2021-02-04 | 2021-06-04 | 95% | Nikhil, Ishaan
8 | R2-I3 | 04. Account Management | 4.01 | View My Account | Check whether account information needs to be updated | 2021-02-04 | 2021-06-04 | 95% | Nikhil, Ishaan
9 | R2-I3 | 04. Account Management | 4.01 | View My Account | Crosscuts: Entitlements | 2021-02-04 | 2021-06-04 | 95% | Nikhil, Ishaan
10 | R2-I3 | 04. Account Management | 4.01 | View My Account | Crosscuts: DF-in, Security | 2021-02-04 | 2021-06-04 | 95% | Nikhil, Ishaan
11 | R2-I3 | 04. Account Management | 4.01 | View My Account | Test 'View My Account' feature | 2021-06-04 |  | 50% | Athauda
12 | R2-I3 | 04. Account Management | 4.02 | Edit Account Information | Allow user to edit their account information | 2021-02-04 | 2021-06-04 | 95% | Nikhil, Ishaan
13 | R2-I3 | 04. Account Management | 4.02 | Edit Account Information | Allow user to update their account information | 2021-02-04 | 2021-06-04 | 95% | Nikhil, Ishaan
14 | R2-I3 | 04. Account Management | 4.02 | Edit Account Information | Crosscuts: Entitlements | 2021-02-04 | 2021-06-04 | 95% | Nikhil, Ishaan
15 | R2-I3 | 04. Account Management | 4.02 | Edit Account Information | Crosscuts: Field Validation, Connectivity | 2021-02-04 | 2021-06-04 | 95% | Nikhil, Ishaan
16 | R2-I3 | 04. Account Management | 4.02 | Edit Account Information | Crosscuts: DF-out, Security | 2021-02-04 | 2021-06-04 | 95% | Nikhil, Ishaan
17 | R2-I3 | 04. Account Management | 4.02 | Edit Account Information | Test 'Edit Account Information' feature | 2021-06-04 |  | 50% | Athauda
18 | R2-I3 | 05. Partner Dashboard | 5.01 | View Partner Information | Allow partner to view their user account information | 2021-02-04 | 2021-06-04 | 100% | Nikhil, Ishaan
19 | R2-I3 | 05. Partner Dashboard | 5.01 | View Partner Information | Check whether user (partner) account information needs to be updated | 2021-02-04 | 2021-06-04 | 100% | Nikhil, Ishaan
20 | R2-I3 | 05. Partner Dashboard | 5.01 | View Partner Information | Crosscuts: Entitlements | 2021-02-04 | 2021-06-04 | 100% | Nikhil, Ishaan
21 | R2-I3 | 05. Partner Dashboard | 5.01 | View Partner Information | Crosscuts: DF-in, Security | 2021-02-04 | 2021-06-04 | 100% | Nikhil, Ishaan
22 | R2-I3 | 05. Partner Dashboard | 5.01 | View Partner Information | Test 'View Partner Information' feature | 2021-06-04 |  | 50% | Athauda
23 | R2-I3 | 05. Partner Dashboard | 5.02 | Edit Partner Information | Allow partner to edit their user account information | 2021-02-04 | 2021-06-04 | 100% | Nikhil, Ishaan
24 | R2-I3 | 05. Partner Dashboard | 5.02 | Edit Partner Information | Allow partner to update their user account information | 2021-02-04 | 2021-06-04 | 100% | Nikhil, Ishaan
25 | R2-I3 | 05. Partner Dashboard | 5.02 | Edit Partner Information | Crosscuts: Entitlements | 2021-02-04 | 2021-06-04 | 100% | Nikhil, Ishaan
26 | R2-I3 | 05. Partner Dashboard | 5.02 | Edit Partner Information | Crosscuts: Field Validation, Connectivity | 2021-02-04 | 2021-06-04 | 100% | Nikhil, Ishaan
27 | R2-I3 | 05. Partner Dashboard | 5.02 | Edit Partner Information | Crosscuts: DF-out, Security | 2021-02-04 | 2021-06-04 | 100% | Nikhil, Ishaan
28 | R2-I3 | 05. Partner Dashboard | 5.02 | Edit Partner Information | Test 'Edit Partner Information' feature | 2021-06-04 |  | 50% | Athauda
R2-I4
29 | R2-I4 | 04. Account Management | 4.03 | Subscription Management | Allow user to choose premium account | 04-16-2021 | 04-30-2021 | 0% | Nikhil, Ishaan
30 | R2-I4 | 04. Account Management | 4.03 | Subscription Management | Allow user to access premium features | 04-16-2021 | 04-30-2021 | 0% | Nikhil, Ishaan
31 | R2-I4 | 04. Account Management | 4.03 | Subscription Management | Crosscuts: Entitlements | 04-16-2021 | 04-30-2021 | 0% | Nikhil, Ishaan
32 | R2-I4 | 04. Account Management | 4.03 | Subscription Management | Crosscuts: Field Validation, Connectivity | 04-16-2021 | 04-30-2021 | 0% | Nikhil, Ishaan
33 | R2-I4 | 04. Account Management | 4.03 | Subscription Management | Crosscuts: DF-out, Security | 04-16-2021 | 04-30-2021 | 0% | Nikhil, Ishaan
34 | R2-I4 | 04. Account Management | 4.03 | Subscription Management | Test 'Subscription Management' feature | 04-16-2021 | 04-30-2021 | 0% | Athauda
35 | R2-I4 | 04. Account Management | 4.04 | Subscription Payment Process | Allow user to make payment in order to subscribe to premium features | 04-16-2021 | 04-30-2021 | 0% | Nikhil, Ishaan
36 | R2-I4 | 04. Account Management | 4.04 | Subscription Payment Process | Allow internal users to keep track of user accounts and generate report | 04-16-2021 | 04-30-2021 | 0% | Nikhil, Ishaan
37 | R2-I4 | 04. Account Management | 4.04 | Subscription Payment Process | Crosscuts: Entitlements | 04-16-2021 | 04-30-2021 | 0% | Nikhil, Ishaan
38 | R2-I4 | 04. Account Management | 4.04 | Subscription Payment Process | Crosscuts: Connectivity, Calculations | 04-16-2021 | 04-30-2021 | 0% | Nikhil, Ishaan
39 | R2-I4 | 04. Account Management | 4.04 | Subscription Payment Process | Crosscuts: DF-in, DF-out, Security | 04-16-2021 | 04-30-2021 | 0% | Nikhil, Ishaan
40 | R2-I4 | 04. Account Management | 4.04 | Subscription Payment Process | Test 'Subscription Payment Process' feature | 04-16-2021 | 04-30-2021 | 0% | Athauda
41 | R2-I4 | 05. Partner Dashboard | 5.03 | Job Posting Management | Allow the partner to post a job, thereby informing about new opening | 04-16-2021 | 04-30-2021 | 0% | Nikhil, Ishaan
42 | R2-I4 | 05. Partner Dashboard | 5.03 | Job Posting Management | Crosscuts: Entitlements | 04-16-2021 | 04-30-2021 | 0% | Nikhil, Ishaan
43 | R2-I4 | 05. Partner Dashboard | 5.03 | Job Posting Management | Crosscuts: Field Validation, Connectivity | 04-16-2021 | 04-30-2021 | 0% | Nikhil, Ishaan
44 | R2-I4 | 05. Partner Dashboard | 5.03 | Job Posting Management | Crosscuts: DF-out, Security | 04-16-2021 | 04-30-2021 | 0% | Nikhil, Ishaan
45 | R2-I4 | 05. Partner Dashboard | 5.03 | Job Posting Management | Test 'Job Posting Management' feature | 04-16-2021 | 04-30-2021 | 0% | Athauda
46 | R2-I4 | 05. Partner Dashboard | 5.04 | View Applicant Report | Allow partner to view the user applications | 04-16-2021 | 04-30-2021 | 0% | Nikhil, Ishaan
47 | R2-I4 | 05. Partner Dashboard | 5.04 | View Applicant Report | Allow partner to shortlist the applications for further recruitment process | 04-16-2021 | 04-30-2021 | 0% | Nikhil, Ishaan
48 | R2-I4 | 05. Partner Dashboard | 5.04 | View Applicant Report | Crosscuts: Entitlements | 04-16-2021 | 04-30-2021 | 0% | Nikhil, Ishaan
49 | R2-I4 | 05. Partner Dashboard | 5.04 | View Applicant Report | Crosscuts: DF-in, Security | 04-16-2021 | 04-30-2021 | 0% | Nikhil, Ishaan
50 | R2-I4 | 05. Partner Dashboard | 5.04 | View Applicant Report | Test 'View Applicant Report' feature | 04-16-2021 | 04-30-2021 | 0% | Athauda