## RCT
| 01. Home |  |  |  |  | 02. Job Management |  |  |  |  | 03. Profile Management |  | 04. Account Management |  |  |  | 05. Partner Dashboard |  |  |  | 06. Help Desk |  | 07. Advertisement Management
| 1.1 User portal (Sign up) | 1.2 User portal (Login) | 1.3 Partner portal (Sign up) | 1.4 Partner portal (Login) | 1.5 Home Search bar | 02.01 Job Search Bar | 02.02 Search Filter | 02.03 Search Results | 02.04 Detailed View | 02.06 Apply | 03.01 View Profile | 03.02 Edit Profile | 04.01 View My Account | 04.02 Edit Account Information | 04.03 Subscription Management | 04.04 Subscription Payment Process | 05.01 View Partner Information | 05.02 Edit Partner Information | 05.03 Job Posting Management | 05.04 View Applicant Report | 06.01 Contact Form | 06.02 FAQ Page | 07.01 Login Page | 07.02 Ad Posting Management | 07.03 Client Information
Core Functionality | 1 | 1 | 1 | 1 | 1 | I1 | I1 | I1 | I2 | I3 | I2 | I2 | I3 | I3 | I4 | I4 | I3 | I3 | I3 | I4 | 1 | 1 | I1 | I2 | I2
GUI Features | 1 | 1 | 1 | 1 | 1 | I1 | I1 | I1 | I2 | I3 | I2 | I2 | I3 | I3 | I4 | I4 | I3 | I3 | I3 | I4 | 1 | 1 | I1 | I2 | I2
Crosscuting Concerns
ET - Entitlements | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | I3 | I2 | I2 | I3 | I3 | I4 | I4 | I3 | I3 | I3 | I4 | 0 | 0 | I1 | I2 | I2
FV - Field Validation | 1 | 1 | 1 | 1 | 1 | I1 | I1 | 0 | 0 | 0 | 0 | I2 | 0 | I3 | I4 | 0 | 0 | I3 | I3 | 0 | 1 | 0 | I1 | 0 | 0
CL - Calculations | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | I4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CC - Concurrency | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | I3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN - Connectivity | 1 | 1 | 1 | 1 | 1 | I1 | I1 | I1 | 0 | I3 | 0 | I2 | 0 | I3 | I4 | I4 | 0 | I3 | I3 | 0 | 1 | 0 | I1 | I2 | 0
DF-In - Data Flow In | 0 | 0 | 0 | 0 | 1 | I1 | I1 | I1 | 0 | 0 | I2 | 0 | I3 | 0 | I4 | 0 | I3 | 0 | 0 | I4 | 0 | 0 | 0 | 0 | I2
DF-Out - Data Flow Out | 0 | 1 | 0 | 1 | 1 | I1 | 0 | I1 | I2 | I3 | 0 | I2 | 0 | I3 | I4 | I4 | 0 | I3 | I3 | 0 | 0 | 0 | I1 | I2 | 0
Security | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | I3 | I2 | I2 | I3 | I3 | I4 | I4 | I3 | I3 | I3 | I4 | 0 | 0 | 0 | I2 | I2
| 01. Home |  |  |  |  | 02. Job Management |  |  |  |  | 03. Profile Management |  | 04. Account Management |  |  |  | 05. Partner Dashboard |  |  |  | 06. Help Desk |  | 07. Advertisement Management
| 1.1 User portal (Sign up) | 1.2 User portal (Login) | 1.3 Partner portal (Sign up) | 1.4 Partner portal (Login) | 1.5 Home Search bar | 02.01 Job Search Bar | 02.02 Search Sort/Filter | 02.03 Search Results | 02.04 Detailed View | 02.06 Apply | 03.01 View Profile | 03.02 Edit Profile | 04.01 View My Account | 04.02 Edit Account Information | 04.03 Subscription Management | 04.04 Subscription Payment Process | 05.01 View Partner Information | 05.02 Edit Partner Information | 05.03 Job Posting Management | 05.04 View Applicant Report | 06.01 Contact Form | 06.02 FAQ Page | 07.01 Login Page | 07.02 Ad Posting Management | 07.03 Client Information
Core Functionality | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
GUI Features | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Crosscuting Concerns
ET - Entitlements | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
CS - Client Setup | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0
FV - Field Validation | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 0
CL - Calculations | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
CC - Concurrency | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CN - Connectivity | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 0
DF-In - Data Flow In | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0
DF-Out - Data Flow Out | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1
SI-In System Interface (inbound) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1
SI-Out - System Interface (outbound) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1
Security | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1

## Application Screen
Search Filter

## UserStory
User Stories
User Story title: | 2.2 Search Filter
User Story description: | As a/an | I want to | so that I can
| Customer | Sort the job listings and filter out the unwanted job categories | View according to my preferences and view the shortlisted job pool

## TD
Use Case (User Story) title | 01.02 Search Filter
Features to be tested | Features to be tested in the context of this use case include: Core Functionality; GUI features; Applicable crosscutting concerns - Field Validation, Connectivity and Data Flow In
Approach refinements (test ideas) | Testing GUI includes testing text input feild, design such as appearance, positioning and colors. Also, GUI Testing needs to be performed on different browsers (Portability testing). Field validation testing is performed based on the equivalence partitioning and boundary value analysis techniques, focusing on invalid (challenging) inputs.
Connectivity is tested by manually disconnecting internet connection
Data Flow In is tested using the Data Flow Chart
| TC No | TC Title
| TC1 | Search Filter - GUI Testing
Test identification | TC2 | Search Filter - Field Validation
| TC3 | Search Filter - Connectivity
| TC4 | Search Filter - Data Flow In
Feature pass/fail criteria | A given test case passed testing if all actual results matched the related expected results. If any of the actual results did not match the expected results, the whole test case has the execution status "Fail". This user story passed testing, if all related test cases have been executed and passed testing.

## TC1
TC Title | TC1: Search Filter - GUI Testing
TC Objective | Ensure the layout and pop-ups appear according to wire-frame layout in different browsers. Input is assumed correct in this TC and Field Validation is tested in TC 3
TC Description | Step | Step Description | Expected Results
| 1 | Verify 'Filter' clickable link appears above the job results | Ensure 'Filter Options' pop-up when clicked on the filter clickable link
| 2 | Verify 'Companies' and 'Job Type' filter options appear | Ensure 'Companies' and 'Job Type' filter options appear in the same horizontal plane
| 3 | Fill both entry fields and click 'Reset' | Both entires should revert back to default

## TC2
TC Title | TC2: Search Filter - Field Validation
TC Objective | To test Search Filter feature with different Filter options and correlate results
TC Description | Step | Step Description | Expected Results
| 1 | Leave 'Companies' and 'Job Type' fields empty and click on 'Submit' | No error message should get poped up
| 2 | Select an option in 'Companies' and 'Job Type' and click 'Submit | No error message should get poped up
| P.S --> | Filter options can be left empty or filled with available options in the drop down menu. Therefore there are no stipulated rules placed by the developers to govern the validity of the entries

## TC3
TC Title | TC 3: Search Filter - Connectivity
TC Objective | To test behaviour when connectivity fails
TC Description | Step | Step Description | Expected Results
| 1 | Disconnect internet connectivity, set filter options and click 'Submit' | User must receive relevant no connection error message of the browser.

## TC4
TC Title | TC4: Search Filter - Data Flow In
TC Objective | This test case validates the data in, search results page should generate results based on the filter options given by the user
TC Description | Step | Step Description | Expected Results
| 1 | Enter a search term and click 'Search' | Search results page should load the appropriate result set.

## Test Execution Log
Test Set | Test Case Title | Status | Exec. Date | Tester's Name
Iteration 1 | TC1. Search Filter - GUI Testing | PASSED | 2021-03-03 | Athauda Dias
Iteration 1 | TC2. Search Filter - Field Validation | PASSED | 2021-03-03 | Athauda Dias
Iteration 1 | TC3. Search Filter - Connectivity | PASSED | 2021-03-03 | Athauda Dias
Iteration 1 | TC4. Search Filter - Data Flow In | PASSED | 2021-03-03 | Athauda Dias