## Road Map
Jobster - Road Map
|  |  | Release 1 |  | Release 2
RCT Modules | Product Backlog | Story Points | Iteration 1 - 2/28/21 | Iteration 2 - 3/26/21 | Iteration 3 - 4/25/21 | Iteration 4 - 5/1/21
01. Home | 1.1 User portal (Sign up) | N/A
| 1.2 User portal (Login) | N/A
| 1.3 Partner portal (Sign up) | N/A
| 1.4 Partner portal (Login) | N/A
| 1.5 Home Search bar | N/A
02. Job Management | 02.01 Job Search Bar | 6 | X
| 02.02 Search Filter | 6 | X
| 02.03 Search Results | 6 | X
| 02.04 Detailed View | 2 |  | X
| 02.05 Apply | 3 |  |  | X
03. Profile Management | 03.01 View Profile | 2 |  | X
| 03.02 Edit Profile | 4 |  | X
04. Account Management | 04.01 View My Account | 2 |  |  | X
| 04.02 Edit Account Information | 4 |  |  | X
| 04.03 Subscription Management | 8 |  |  |  | X
| 04.04 Subscription Payment Process | 8 |  |  |  | X
05. Partner Dashboard | 05.01 View Partner Information | 2 |  |  | X
| 05.02 Edit Partner Information | 4 |  |  | X
| 05.03 Job Posting Management | 6 |  |  | X
| 05.04 View Applicant Report | 2 |  |  |  | X
06. Help Desk | 06.01 Contact Form | N/A
| 06.02 FAQ Page | N/A
07. Advertisement Management | 07.01 Login Page | 3 | X
| 07.02 Ad Posting Management | 6 |  | X
| 07.03 Client Information | 4 |  | X
| 07.04 Add Client Information | 3 |  | X
|  | VELOCITY: | 21 | 21 | 21 | 18

## Story Map
Epics |  | Epic 1 - Job Management | Epic 2 - Profile Management | Epic 3 - Account Management | Epic 4 - Partner Dashboard | Epic 5 - Advertisement Management
Epic 1 - Job Management Epic 2 - Profile Management Epic 3 - Account Management Epic 4 - Partner Dashboard Epic 5 - Advertisement Management | User Stories | 2.1 Job Search Bar 2.2 Search Sort/Filter 2.3 Search Results |  |  |  | 7.1 Login Page | Iteration 1
|  | 2.4 Detailed View | 3.1 View Profile 3.2 Edit Profile |  |  | 7.2 Ad Posting Management 7.3 Client Information 7.4 Add Client Information | Iteration 2
|  | 2.5 Apply |  | 4.1 View My Account 4.2 Edit Account Information | 5.1 View Partner Information 5.2 Edit Partner Information 5.3 Job Posting Management |  | Iteration 3
|  |  |  | 4.3 Subscription Management 4.4 Subscription Payment Process | 5.4 View Applicant Report |  | Iteration 4