## Sheet1
Task # | Iteration | Module Name | RCT ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner
1 | R1-I1 | 02. Job Management | 2.01 | Job Search Bar | Allow user to input text | 02-20-2021 | 02-22-2021 | 100% | Nikhil
2 | R1-I1 | 02. Job Management | 2.01 | Job Search Bar | Accept the user input and display the resultant pool based in user input | 02-20-2021 | 02-23-2021 | 100% | Nikhil
3 | R1-I1 | 02. Job Management | 2.01 | Job Search Bar | Crosscuts: Connectivity | 02-20-2021 | 02-28-2021 | 100% | Nikhil
4 | R1-I1 | 02. Job Management | 2.02 | Search Filter | Allow user to input the sorting criteria | 02-20-2021 | 02-24-2021 | 100% | Nikhil
5 | R1-I1 | 02. Job Management | 2.02 | Search Filter | Display the shortlisted pool of jobs based on user preferences | 02-20-2021 | 02-25-2021 | 100% | Nikhil
6 | R1-I1 | 02. Job Management | 2.02 | Search Filter | Crosscuts: Connectivity | 02-20-2021 | 02-25-2021 | 100% | Nikhil
7 | R1-I1 | 02. Job Management | 2.03 | Search Results | Display the job pool based on user input | 02-20-2021 | 02-23-2021 | 100% | Nikhil
8 | R1-I1 | 02. Job Management | 2.03 | Search Results | Crosscuts: Connectivity, DF-in | 02-20-2021 | 02-23-2021 | 100% | Nikhil
9 | R1-I1 | 07. Advertisement Management | 7.01 | Login Page | Implement a GUI for internal user login | 02-20-2021 | 2021-02-03 | 100% | Ishaan
10 | R1-I1 | 07. Advertisement Management | 7.01 | Login Page | Redirect to logged in page | 02-20-2021 | 2021-02-03 | 100% | Ishaan
11 | R1-I1 | 07. Advertisement Management | 7.01 | Login Page | Crosscuts: Entitlements | 02-20-2021 | 2021-02-03 | 100% | Ishaan
12 | R1-I1 | 07. Advertisement Management | 7.01 | Login Page | Crosscuts: Connectivity | 02-20-2021 | 2021-02-03 | 100% | Ishaan
13 | R1-I1 | 07. Advertisement Management | 7.01 | Login Page | Crosscuts: Data Dependency Validation | 02-20-2021 | 2021-02-03 | 100% | Ishaan
14 | R1-I2 | 02. Job Management | 2.04 | Detailed View | Allow user to expand the compact search results | 2021-01-03 | 03-20-2021 | 100% | Nikhil
15 | R1-I2 | 02. Job Management | 2.04 | Detailed View | Display the detailed view (expanded version) of selected job | 2021-01-03 | 03-20-2021 | 100% | Nikhil
16 | R1-I2 | 03. Profile Management | 3.01 | View Profile | Implement GUI to allow user to view profile | 2021-01-03 | 03-25-2021 | 100% | Nikhil
17 | R1-I2 | 03. Profile Management | 3.01 | View Profile | Redirect to user account page | 2021-01-03 | 03-25-2021 | 100% | Nikhil
18 | R1-I2 | 03. Profile Management | 3.01 | View Profile | Display the user profile | 2021-01-03 | 03-25-2021 | 100% | Nikhil
19 | R1-I2 | 03. Profile Management | 3.01 | View Profile | Crosscuts: Entitlements, DF-in | 2021-01-03 | 03-25-2021 | 100% | Nikhil
20 | R1-I2 | 03. Profile Management | 3.01 | View Profile | Crosscuts: Security | 2021-01-03 | 03-25-2021 | 100% | Nikhil
21 | R1-I2 | 03. Profile Management | 3.02 | Edit Profile | Implement GUI for editable fields | 2021-01-03 | 03-25-2021 | 100% | Nikhil
22 | R1-I2 | 03. Profile Management | 3.02 | Edit Profile | Allow user to edit profile details | 2021-01-03 | 03-25-2021 | 100% | Nikhil
23 | R1-I2 | 03. Profile Management | 3.02 | Edit Profile | Crosscuts: Entitlements, field validation | 2021-01-03 | 03-25-2021 | 100% | Nikhil
24 | R1-I2 | 03. Profile Management | 3.02 | Edit Profile | Crosscuts: Connectivity, DF-out, Security | 2021-01-03 | 03-25-2021 | 100% | Nikhil
25 | R1-I2 | 07. Advertisement Management | 7.02 | Ad Posting Management | Implement UI for advertisement upload | 2021-01-03 | 03-25-2021 | 100% | Ishaan
26 | R1-I2 | 07. Advertisement Management | 7.02 | Ad Posting Management | Allow internal user to upload advertisement | 2021-01-03 | 03-25-2021 | 100% | Ishaan
27 | R1-I2 | 07. Advertisement Management | 7.02 | Ad Posting Management | Display ads on the portal | 2021-01-03 | 03-25-2021 | 100% | Ishaan
28 | R1-I2 | 07. Advertisement Management | 7.02 | Ad Posting Management | Crosscuts: Entitlements | 2021-01-03 | 03-25-2021 | 100% | Ishaan
29 | R1-I2 | 07. Advertisement Management | 7.02 | Ad Posting Management | Crosscuts: Connectivity, DF-out, Security | 2021-01-03 | 03-25-2021 | 100% | Ishaan
30 | R1-I2 | 07. Advertisement Management | 7.03 | Client Information | Create an UI for client information display | 2021-01-03 | 03-20-2021 | 100% | Nikhil, Ishaan
31 | R1-I2 | 07. Advertisement Management | 7.03 | Client Information | Display the client info to keep an account of revenue generated | 2021-01-03 | 03-20-2021 | 100% | Nikhil, Ishaan
32 | R1-I2 | 07. Advertisement Management | 7.03 | Client Information | Crosscuts: Entitlements | 2021-01-03 | 03-20-2021 | 100% | Nikhil, Ishaan
33 | R1-I2 | 07. Advertisement Management | 7.03 | Client Information | Crosscuts: DF-in, Security | 2021-01-03 | 03-20-2021 | 100% | Nikhil, Ishaan
33 | R1-I2 | 07. Advertisement Management | 7.04 | Add Client Information | Allow user to add new clients to database | 03-24-2021 | 03-26-2021 | 100% | Nikhil, Ishaan
33 | R1-I2 | 07. Advertisement Management | 7.04 | Add Client Information | Crosscuts: Entitlements, Field validation | 03-24-2021 | 03-26-2021 | 100% | Nikhil, Ishaan
33 | R1-I2 | 07. Advertisement Management | 7.04 | Add Client Information | Crosscuts: Connectivity, DF-out | 03-24-2021 | 03-26-2021 | 100% | Nikhil, Ishaan