## Sheet1
Iteration | Module | Title | As a/an | I want to... | So that I can... | Iteration | Story Points | Story Constraints
FALL | 01. Home | 1.1 User portal (Sign up) | Customers | Create an user account | Have an account | Last Semester | Last Semester
|  | 1.2 User portal (Login) | Customers | Log into my account | Login to account and access the profile | Last Semester | Last Semester
|  | 1.3 Partner portal (Sign up) | HR | Create a partner account | Have an account | Last Semester | Last Semester
|  | 1.4 Partner portal (Login) | HR | Log into my account | Post latest job openings in the company | Last Semester | Last Semester
|  | 1.5 Home Search bar | Customers | Access the job openings | View the list of jobs | Last Semester | Last Semester
SPRING | 02. Job Management | 2.1 Job Search bar | Customers, Help Desk and Operations Manager | Access the job openings | Apply for the job | I1 | 6 | Possibility that no matching job listings are found | ITERATION 1
|  | 2.2 Search Sort/Filter | Customers, Help Desk and Operations Manager | Sort the job listings and filter out the unwanted job categories | View according to my preferences and view the shortlisted job pool | I1 | 6 | Customers should only be able to use sort/filter functions provided by Jobster. | ITERATION 2
|  | 2.3 Search results | Customers, Help Desk and Operations Manager | View listed jobs | Choose job listing that suits my career interests. | I1 | 6 | Customer may not find any jobs based on their search criteria
|  | 2.4 Detailed view | Customers, Help Desk and Operations Manager | View the detailed job description | Get the insights about the job and the company | I2 | 2 | Customer can only view one detailed view at a time
|  | 2.5 Apply | Customers, Help Desk and Operations Manager | Apply to the job opening | Send my application to the recruiter | I3 | 3
| 03 Profile Management | 3.1 View Profile | Customers, HR, Help Desk and Operations Manager, Account Manager | View my profile | Confirm whether my profile is up-to-date | I2 | 2 | Customers may only have one profile and certain data fields are required for all profiles
|  | 3.2 Edit Profile | Customers, HR, Help Desk and Operations Manager, Account Manager | Edit my profile | Update my profile | I2 | 4 | Can make unlimited changes to profile at once but changes cannot be undone.
| 04. Account Management | 4.1 View my account | Customers, HR, Help Desk and Operations Manager, Account Manager | View my account info | Check whether my account info needs an updation | I3 | 2
|  | 4.2 Edit account information | Customers, HR, Help Desk and Operations Manager, Account Manager | Edit my account info | Update my account information | I3 | 4
|  | 4.3 Subscription management | Customers, Sales Manager, Marketing Manager, Financial Analyst, Accountant, Account Manager | Premium account | Access to premium features | I4 | 8
|  | 4.4 Subscription payment process | Customers | Make a payment | Subscribe to premium account | I4 | 8
|  |  | Account Manager, Accountant, Financial Analyst, Sales Manager | Keep a track of all the user accounts | Analyse and generate report on user base | I4 | 8
| 05. Partner Dashboard | 5.1 View partner information | HR, Account Manager | View my information | Check whether information needs to be updated. | I3 | 2
|  | 5.2 Edit partner information | HR, Account Manager | Edit my information | Make sure everything is updated | I3 | 4
|  | 5.3 Job Posting Management | HR, Account Manager | Post the job | Inform about the latest opening | I3 | 6
|  | 5.4 View Applicant Report | HR, Sales Manager, Marketing Manager, Account Manager | View the list of applications | Shortlist potential applicants for subsequent recruitment process | I4 | 2
FALL | 06. Help Desk | 6.1 Contact Form | Customers | Connect with support representative | Resolve my grievances | Last Semester | Last Semester
|  | 6.2 FAQ page | Customers | List out the common FAQs | Reduce the time to address customer grievances | Last Semester | Last Semester
SPRING | 07. Advertisement Management | 7.1 Login page | Marketing Manager, Sales Manager, Media Relations Specialist | Login to Advertisement Management Account | Use account to push an advertisement into the feed | I1 | 3 | Jobseekers should not be able to access portal with their user login information
|  | 7.2 Ad posting Management | Marketing Manager, Sales Manager, Media Relations Specialist, Accountant, Financial Analyst | Feature the ad on the platform | Generate the revenue for the company | I2 | 6 | Customers should only be able to advertise if they send their ad postings via e-mail.
|  | 7.3 Client Information | Marketing Manager, Sales Manager, Media Relations Specialist, Accountant, Financial Analyst, Help desk and Operations Manager | Keep an account of revenue generated by advertisements | Generate the balance sheet for tax purposes | I2 | 4 | Information should not be visible to Customers at any time
|  | 7.4 Add Client Information | Marketing Manager, Sales Manager, Media Relations Specialist, Accountant, Financial Analyst, Help desk and Operations Manager | Add client information | So that the admin can add a new clients to the database | I2 | 4 | Customers should not be able to add client information